## Team To-Do List
Task ID | Phase | Task Name | Assigned To | Priority | Status | Start Date | Due Date | Progress (%) | Dependencies | Notes
T-001 | Initiation | Define project charter | Tristan | High | Complete | 2025-08-18 | 2025-08-20 | 100 |  | Approved by sponsor
T-002 | Initiation | Identify stakeholders | Aisha | Medium | Complete | 2025-08-18 | 2025-08-22 | 100 | T-001 | Stakeholder register v1
T-003 | Planning | Develop project plan | Zara | High | In Progress | 2025-08-23 | 2025-09-01 | 60 | T-001 | Scope, schedule, budget
T-004 | Planning | Build WBS & estimates | Sam | Medium | In Progress | 2025-08-25 | 2025-09-05 | 45 | T-003 | Estimation workshop
T-005 | Execution | Set up dev environment | Lebo | High | Complete | 2025-08-28 | 2025-08-30 | 100 | T-004 | Repos & CI pipeline
T-006 | Execution | Feature A implementation | Zara | High | In Progress | 2025-08-30 | 2025-09-22 | 35 | T-004 | Sprint 1 & 2
T-007 | Execution | Feature B implementation | Sam | Medium | Not Started | 2025-09-07 | 2025-10-02 | 0 | T-006 | Depends on API
T-008 | Monitoring & Control | Weekly status reports | Tristan | Low | In Progress | 2025-08-25 | 2025-10-27 | 40 |  | Every Friday
T-009 | Monitoring & Control | QA & testing cycle 1 | Aisha | High | Not Started | 2025-09-19 | 2025-10-03 | 0 | T-006 | Test plan v1
T-010 | Monitoring & Control | Risk review & mitigation | Tristan | Medium | In Progress | 2025-09-02 | 2025-10-22 | 30 |  | Update risk log
T-011 | Closure | Training & handover | Lebo | Medium | Not Started | 2025-10-09 | 2025-10-17 | 0 | T-009 | User training pack
T-012 | Closure | Project retrospective | Team | Low | Not Started | 2025-10-18 | 2025-10-23 | 0 | T-011 | Lessons learned

## Simplified View
Task Name | Owner | Status | Due | % | Notes
Define project charter | Tristan | Complete | 2025-08-20 | 100 | Approved by sponsor
Identify stakeholders | Aisha | Complete | 2025-08-22 | 100 | Stakeholder register v1
Develop project plan | Zara | In Progress | 2025-09-01 | 60 | Scope, schedule, budget
Build WBS & estimates | Sam | In Progress | 2025-09-05 | 45 | Estimation workshop
Set up dev environment | Lebo | Complete | 2025-08-30 | 100 | Repos & CI pipeline
Feature A implementation | Zara | In Progress | 2025-09-22 | 35 | Sprint 1 & 2
Feature B implementation | Sam | Not Started | 2025-10-02 | 0 | Depends on API
Weekly status reports | Tristan | In Progress | 2025-10-27 | 40 | Every Friday
QA & testing cycle 1 | Aisha | Not Started | 2025-10-03 | 0 | Test plan v1
Risk review & mitigation | Tristan | In Progress | 2025-10-22 | 30 | Update risk log
Training & handover | Lebo | Not Started | 2025-10-17 | 0 | User training pack
Project retrospective | Team | Not Started | 2025-10-23 | 0 | Lessons learned

## Gantt - Weekly
Task Name | Phase | Assigned To | Start Date | End Date | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01
Define project charter | Initiation | Tristan | 2025-08-18 | 2025-08-20
Identify stakeholders | Initiation | Aisha | 2025-08-18 | 2025-08-22
Develop project plan | Planning | Zara | 2025-08-23 | 2025-09-01
Build WBS & estimates | Planning | Sam | 2025-08-25 | 2025-09-05
Set up dev environment | Execution | Lebo | 2025-08-28 | 2025-08-30
Feature A implementation | Execution | Zara | 2025-08-30 | 2025-09-22
Feature B implementation | Execution | Sam | 2025-09-07 | 2025-10-02
Weekly status reports | Monitoring & Control | Tristan | 2025-08-25 | 2025-10-27
QA & testing cycle 1 | Monitoring & Control | Aisha | 2025-09-19 | 2025-10-03
Risk review & mitigation | Monitoring & Control | Tristan | 2025-09-02 | 2025-10-22
Training & handover | Closure | Lebo | 2025-10-09 | 2025-10-17
Project retrospective | Closure | Team | 2025-10-18 | 2025-10-23

## Gantt - Monthly
Task Name | Phase | Assigned To | Start Date | End Date | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
Define project charter | Initiation | Tristan | 2025-08-18 | 2025-08-20
Identify stakeholders | Initiation | Aisha | 2025-08-18 | 2025-08-22
Develop project plan | Planning | Zara | 2025-08-23 | 2025-09-01
Build WBS & estimates | Planning | Sam | 2025-08-25 | 2025-09-05
Set up dev environment | Execution | Lebo | 2025-08-28 | 2025-08-30
Feature A implementation | Execution | Zara | 2025-08-30 | 2025-09-22
Feature B implementation | Execution | Sam | 2025-09-07 | 2025-10-02
Weekly status reports | Monitoring & Control | Tristan | 2025-08-25 | 2025-10-27
QA & testing cycle 1 | Monitoring & Control | Aisha | 2025-09-19 | 2025-10-03
Risk review & mitigation | Monitoring & Control | Tristan | 2025-09-02 | 2025-10-22
Training & handover | Closure | Lebo | 2025-10-09 | 2025-10-17
Project retrospective | Closure | Team | 2025-10-18 | 2025-10-23

## Legend & Lookups
Legend
Lifecycle Phases:
Initiation → Planning → Execution → Monitoring & Control → Closure
Priority colour code:
High = Red
Medium = Amber
Low = Green
Status options:
Not Started, In Progress, At Risk, Blocked, Complete
Tips:
• Add tasks in 'Team To-Do List'. Gantt updates from dates.
• Use filters on headers to focus by owner, phase, or status.
• Update Progress (%) regularly. Data bars give quick cues.

## Instructions
Team To-Do & Gantt Tracker – Instructions
1) Overview
This workbook helps manage tasks across the full project lifecycle and automatically generates Weekly and Monthly Gantt charts for clear visual tracking.
2) How to Add or Edit Tasks
1. Go to Team To-Do List.
2. Fill in:
Task ID – unique code for the task
Phase – Initiation, Planning, Execution, Monitoring & Control, Closure
Task Name – short but descriptive
Assigned To – must match names in Lookups for dropdown to work
Priority – High, Medium, Low (colour-coded)
Status – Not Started, In Progress, At Risk, Blocked, Complete
Start Date and Due Date – determines Gantt chart shading
Progress (%) – 0–100 (shows data bar for quick view)
Dependencies – Task IDs that must finish first
Notes – any extra info, links, or context
3) Priority Colour Codes
High → Red
Medium → Amber
Low → Green
These colours apply automatically in the Priority column of both the master and simplified sheets.
4) Gantt Charts
Gantt – Weekly → 16 weeks from the project start date (dummy data starts 18 Aug 2025)
Gantt – Monthly → Jan–Dec 2025 view
Shaded bars appear when a task’s Start Date and Due Date overlap the week/month columns.
5) Simplified View
Read-only summary of key columns from the main To-Do List.
Useful for quick stand-ups and progress reviews without extra detail.
6) Tips for Best Use
Keep dates and statuses up to date – the Gantt charts rely on them.
Use filters on headers to focus on specific owners, priorities, or phases.
Check dependencies to avoid delays.
To extend the Gantt chart time range, add more week/month columns and copy the conditional formatting.